## Slide 1
SL
SwiftLog Logistics Analytics & AI Transformation
Project Management Capstone | AnalystLab Africa, Week 5
Presented by Lamiaa Samraoui, Project Manager
Notes: Introduce yourself as the Project Manager of the SwiftLog Logistics Analytics and AI Transformation Project. Explain that you coordinated five tracks: Data Analytics, Data Science, Machine Learning, GenAI, and QA. Say this talk covers how the project was planned, governed, and delivered.

## Slide 2
The business problem
!
63.7%
of shipments delayed, averaging 5.03 days
i
26.2%
of demand from Ibadan, with 0 local hubs
!
1,626
shipments attached to cancelled orders
Notes: Nearly two thirds of shipments arrive late, by about five days on average. Ibadan generates over a quarter of demand yet has no local hub, which we call the Ibadan Deficit. In addition, 1,626 shipments were attached to cancelled orders, a data integrity issue.

## Slide 3
Objectives and scope
✓
✕
In scope
Out of scope
Data cleaning and dashboards
Feature engineering and ML models
GenAI assistant and QA testing
Supplier performance scoring
Warehouse capacity utilisation
Both exclusions formally logged via change request.
Notes: In scope were cleaning, dashboards, feature engineering, ML models, the GenAI assistant, and QA. Supplier scoring and warehouse capacity were excluded because the data lacks a supplier link and a capacity field. Both exclusions went through a formal change request.

## Slide 4
Project plan overview: WBS
1.0
Initiation & Governance
2.0
Data Preparation
3.0
Data Analytics
4.0
Data Science & ML
5.0
Generative AI
6.0
QA & Testing
7.0
Project Closure
Team & Resources
5 Interns (PM + 4 Track Leads)
40 hours per intern during Week 5 (200 total project hours)
$0 tooling cost (Open-source: Python, Power BI, FastAPI)
Notes: The work breaks into seven packages, from initiation to closure. Cleaned data feeds the dashboards and the feature matrix, which feed the models and the GenAI assistant. The team was five interns, the PM plus four track leads, at 40 hours each during Week 5, about 200 project hours, with $0 tooling cost.

## Slide 5
7-Day Execution Timeline (Week 5)
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
Data Cleaning (DS/DA)
Dashboards (DA)
Features & Models (DS/ML)
RAG & Integration (GenAI)
QA & PM Reporting
Milestones
M1
M2
M3
M4
M5
Days 1-2: Data Cleaning (DS/DA)
Days 3-4: Dashboards & Features
Days 5-6: ML & GenAI Deployment
Day 7: QA & Final Submission
Milestones: M1 (Day 2), M2 (Day 3), M3 (Day 5), M4 (Day 6), M5 (Day 7)
Notes: The project was executed in seven days during Week 5 of the internship. Data cleaning and dashboards ran first, then features and models, then RAG development and integration, then QA and reporting. Milestones M1 to M5 fell on days 2, 3, 5, 6 and 7, with the final submission on Sunday at 11:59 PM WAT.

## Slide 6
Risk management: heat map
R9
R5 R10
R1 R3 R4
R2 R6 R7
R8
High
Med
Low
Low
Med
High
Probability
Impact
R1 Ibadan Deficit (High/High)
R2 Revenue Conflict (High/Medium)
R3 Cancelled shipments (High/High)
R4 Supplier data gap (High/High)
R5 ML misalignment (Medium/Medium)
Full 10-risk register is in the Excel workbook.
Notes: The heat map plots all ten risks by probability and impact. The Ibadan Deficit, cancelled shipments, and the supplier gap score nine, the highest. The Revenue Conflict between $19.1M gross and $14.44M confirmed is mitigated by standardising KPI definitions.

## Slide 7
Governance structure
Sponsor: AnalystLab Africa
PM: Lamiaa Samraoui
DA Lead
DS Lead
ML Lead
GenAI Lead
Escalation: lead, then PM, then Sponsor.
Notes: The Sponsor approves scope changes, the PM runs daily execution, and four track leads own their deliverables. Issues escalate from lead to PM to Sponsor. Documents follow draft, PM review, then Sponsor approval.

## Slide 8
Stakeholder engagement
Keep satisfied
Manage closely
SwiftLog Management, Sponsor
Monitor
Keep informed
DA, DS, ML, GenAI leads
Vertical: power (low to high going up). Horizontal: interest (low to high going right).
Notes: Management and the Sponsor have high power and high interest, so they get weekly executive summaries. Track leads have high interest but less formal power, so they get daily stand-ups. This keeps dependencies, such as DS features feeding ML, on schedule.

## Slide 9
Monitoring and control dashboard
24/24
Pytests passing
$19.1M
gross revenue
63.7%
delay rate
0.9650
forecast R²
Track status
DA: delivered
DS: delivered
ML: delivered
GenAI: delivered
QA: delivered
SPI 1.0 | 0% variance | $0 spent
Notes: All five tracks are green, 24 of 24 tests pass, and schedule performance is 1.0 with zero percent variance. Spend was zero dollars. Remind the audience that $19.1M is gross revenue and $14.44M is confirmed.

## Slide 10
Agile approach: Kanban
To Do
Hub feasibility study
KPI definition sheet
In Progress
ML target realignment
Done
Data cleaning
Dashboards
Feature matrix
Demand forecaster
RAG assistant
24/24 tests
Short sprints absorbed data surprises.
Notes: Short sprints let the team react when the data gaps and the weak delay model appeared. The board shows completed work and the open follow-ups. Agile fits AI work because the real constraints emerge during delivery.

## Slide 11
Outcomes delivered
$19.1M
gross revenue across 4,600 processed orders
R² 0.9650
Gradient Boosting demand forecaster (MAE $286.14)
24/24
QA Pytests passing (100%)
Also delivered: feature matrix, 20 prompt templates, RAG assistant, 3 workflows.
Notes: The forecaster reached R² 0.9650 with a mean absolute error of $286.14. Revenue of $19.1M is gross list-price revenue across 4,600 orders. QA passed all 24 tests.

## Slide 12
Recommendations
1
Close Ibadan Hub Gap
Feasibility study
2
Fix Data Foundations
Add SupplierID & Capacity fields
3
Standardize KPIs
Gross vs Confirmed revenue
4
Realign ML Targets
Fix delay prediction
5
Deploy GenAI with Oversight
RAG assistant
Full list of 10 recommendations available in the PM Report.
Notes: Here are the top five of ten recommendations. First, a feasibility study for an Ibadan hub, which serves 26.2% of demand. Second, fix the data foundations, then standardise revenue KPIs, realign the delay model, and deploy the GenAI tools with oversight. The full list of ten is in the PM report.

## Slide 13
Conclusion and next steps
All five tracks delivered; QA passed.
Key findings: Ibadan, delays, data gaps.
Next: hub study, KPIs, governance.
→
Notes: All five tracks delivered and passed QA. The key findings are the Ibadan Deficit, the delay rate, and the data gaps. The next steps are the hub study, a single KPI standard, and data governance fixes.

## Slide 14
Thank you
Questions and discussion
Lamiaa Samraoui, Project Manager
GitHub: [Insert GitHub URL] | LinkedIn: [Insert LinkedIn URL]
Notes: Thank the audience and the four track leads, then invite questions. Replace the two placeholders with your GitHub and LinkedIn links before presenting.