## Risk Register
Risk ID | Risk Description | Probability | Impact | Score | Response Strategy | Owner
R1 | Ibadan Deficit: 26.2% of demand with 0 local hubs | High | High | 9 | Commission a hub feasibility study | PM
R2 | Revenue Conflict: $19.1M gross (DA) vs $14.44M confirmed (DS) | High | Medium | 6 | Standardize KPI definitions; label Gross vs Confirmed | PM
R3 | Cancelled Order Shipments: 1,626 shipments on cancelled orders | High | High | 9 | Add dashboard disclaimers; flag for data governance | DA Lead
R4 | Supplier Data Gap: no foreign key linking suppliers to shipments | High | High | 9 | Formally exclude from scope; recommend data fix | PM
R5 | ML Target Misalignment: delay AUC 0.52 vs forecast R² 0.9650 | Medium | Medium | 4 | Realign ML targets with business questions | ML Lead
R6 | Warehouse Capacity Missing: no capacity field | High | Medium | 6 | Use stock levels as a proxy | PM
R7 | Revenue Basis: list price ignores discounts and tax | High | Medium | 6 | Label all revenue as indicative | DA Lead
R8 | Return Rates Approximate: returns link to orders not products | High | Low | 3 | Add footnotes to return visuals | DA Lead
R9 | Synthetic Data Limits: models trained on synthetic baselines | Medium | High | 6 | Present models as baselines not production-ready | ML Lead
R10 | Integration Delays: cross-track dependencies cause bottlenecks | Medium | Medium | 4 | Weekly syncs and clear escalation paths | PM
Score = Probability x Impact (Low=1, Medium=2, High=3). Owners are proposed by role.

## RACI Matrix
Task | PM (Lamiaa) | DA Lead | DS Lead | ML Lead | GenAI Lead | Sponsor
Data Cleaning | I | R | A/R | I | I | I
Dashboard Build | I | A/R | C | I | I | I
Model Training | I | I | C | A/R | I | I
RAG Assistant | I | I | C | C | A/R | I
QA & Testing | A | R | R | R | R | I
Final Report | A/R | C | C | C | C | I
R = Responsible, A = Accountable, C = Consulted, I = Informed.

## Issue Log
Issue ID | Description | Priority | Owner | Status | Resolution
I1 | 1,626 shipments attached to cancelled orders (data integrity) | High | DA Lead | Closed | Dashboard disclaimer added; flagged for data governance
I2 | Revenue discrepancy: $19.1M gross (DA) vs $14.44M confirmed (DS) | High | PM | Closed | Standard definitions published: Gross vs Confirmed
I3 | No supplier foreign key and no warehouse capacity field | High | PM | Closed | Both analyses excluded from scope via change request
I4 | Delay classifier weak (AUC 0.52) | Medium | ML Lead | Open | Present as baseline; realign target before operational use

## Assumption Log
ID | Assumption | Owner | Validation Status
A1 | LineRevenue = Quantity x UnitPrice (list price with no discounts or taxes) | DA Lead | Accepted
A2 | Delayed = 3-7 days | DS Lead | Accepted
A3 | Band thresholds (150/350) are acceptable | DA Lead | To Confirm
A4 | Datasets are structurally sound aside from logged issues | DS Lead | Accepted
A5 | Order-level return rates are an adequate approximation | DA Lead | Accepted

## Dependency Log
ID | Dependency | From | To | Status
D1 | Cleaned data | DS | DA, ML | Delivered
D2 | 38-variable feature matrix | DS | ML | Delivered
D3 | Trained ML models | ML | GenAI | Delivered
D4 | Approval of scope exclusions | PM | Sponsor | Closed

## Change Log
Change ID | Description | Requestor | Approved By | Status
C1 | Exclude supplier scoring (no supplier foreign key) | PM | Sponsor | Approved
C2 | Exclude warehouse capacity utilisation (no capacity field) | PM | Sponsor | Approved
C3 | Add Ibadan Deficit to Risk Register | PM | Sponsor | Approved

## Product Backlog
Story ID | User Story | Priority | Sprint | Status
US1 | As a DA I want 11 tables cleaned so dashboards are reliable | High | 1 | Done
US2 | As a manager I want a dashboard of revenue and delays so I can act on delivery performance | High | 2 | Done
US3 | As an ML lead I want a 38-variable feature matrix so I can train models | High | 2 | Done
US4 | As a manager I want a demand forecaster so I can plan stock | High | 3 | Done
US5 | As an ops user I want a delay classifier so risky shipments are flagged | Medium | 3 | Done
US6 | As an ops user I want a grounded RAG assistant so I can query logistics data | High | 3 | Done
US7 | As a manager I want three automated workflows (Daily Briefing / Delay Scanner / Auto-Restock) so reporting is automatic | Medium | 3 | Done
US8 | As a PM I want 24/24 Pytests passing so delivery is safe | High | 4 | Done
Sprint 1 (Days 1-2) = Data Prep, Sprint 2 (Days 3-4) = Analytics & Features, Sprint 3 (Days 5-6) = ML & GenAI Deployment, Sprint 4 (Day 7) = QA & Reporting.

## Stakeholder Register
Name | Role | Interest | Power | Engagement Strategy
SwiftLog Management | Client | High | High | Manage closely: weekly executive summaries and final presentation
AnalystLab Africa | Sponsor | High | High | Manage closely: weekly update; approves scope exclusions
DA Lead | Data Analytics track | High | Medium | Keep informed: daily Slack stand-ups and dependency log
DS Lead | Data Science track | High | Medium | Keep informed: daily Slack stand-ups and dependency log
ML Lead | Machine Learning track | High | Medium | Keep informed: daily Slack stand-ups and dependency log
GenAI Lead | GenAI track | High | Medium | Keep informed: daily Slack stand-ups and dependency log

## Resource Allocation
Resource | Role | Phase 1: Data (Days 1-2) | Phase 2: Analytics (Days 3-4) | Phase 3: ML/GenAI (Days 5-6) | Phase 4: QA & Report (Day 7)
Lamiaa S. (PM) | Project Manager | 100% | 100% | 100% | 100%
Franklin (DA) | Data Analytics Lead | 100% | 100% | 100% | 100%
Uno / Victoria (DS) | Data Science Lead | 100% | 100% | 100% | 100%
Yassine / Zaid (ML) | Machine Learning Lead | 100% | 100% | 100% | 100%
Dorsin (GenAI) | GenAI Lead | 0% | 50% | 100% | 100%
Total hours = 200 (1 week x 40 hours x 5 interns).

## Change Request Form
Field | Entry
Change Request ID | CR-001
Date Requested | [To Confirm]
Requested By | Lamiaa Samraoui, Project Manager
Description of Change | Exclude Supplier Performance Scoring from project scope
Reason for Change | Data lacks a foreign key linking suppliers to products or shipments, so scoring cannot be calculated reliably
Impact Analysis | Scope: supplier scoring removed from deliverables. Schedule: no impact. Budget: no impact ($0 tooling). Quality: prevents inaccurate supplier reporting. Follow-up: add SupplierID to data collection (Recommendations 2 and 7).
Decision | Approved
Approved By | AnalystLab Africa Programme Director (Sponsor)
Date Approved | [To Confirm]
Warehouse capacity utilisation was excluded the same way (Change Log C2): no capacity field exists.

## Lessons Learned
ID | Lesson Learned | Category | Recommendation for Future | Owner
LL1 | Revenue definitions differed between tracks: DA reported $19.1M gross while DS reported $14.44M confirmed | Requirements / KPI definition | Define KPIs such as revenue, and publish one shared definition sheet, before analysis begins | PM
LL2 | Missing data fields (supplier link, warehouse capacity) were found only during delivery | Data quality / Scoping | Audit required data fields against the Data Dictionary at project kickoff | PM
LL3 | ML target misalignment: delay prediction was weak (AUC 0.52) while demand forecasting was strong (R² 0.9650) | Technical / ML | Align ML targets with the business question early and review them at each sprint | ML Lead

## Decision Log
Decision ID | Date | Description | Rationale | Approver
D-01 | [To Confirm] | Report revenue as Gross ($19.1M) and Confirmed ($14.44M), clearly labelled | DA and DS figures differ because 1,626 shipments are attached to cancelled orders; both are valid under their own definitions | PM (Lamiaa Samraoui)
D-02 | [To Confirm] | Exclude supplier performance scoring and warehouse capacity utilisation from scope | No supplier foreign key and no capacity field exist; analysis would be inaccurate | Sponsor (AnalystLab Africa)

## Sprint Templates
Sprint Backlog
Sprint | Goal | Items Included | Status
Sprint 1 (Days 1-2) | Data Prep | Clean 11 tables (36,115 records) | Done
Sprint 2 (Days 3-4) | Analytics & Features | BI dashboards; 38-variable feature matrix | Done
Sprint 3 (Days 5-6) | ML & GenAI Deployment | Demand forecaster; delay classifier; RAG assistant | Done
Sprint 4 (Day 7) | QA & Reporting | 24/24 Pytests; PM Final Report; Presentation | Done
Sprint Review Template (Sprints 3-4)
Question | Answer
Which stories were completed? | Forecaster, delay classifier, RAG assistant, three workflows, and QA (US4 to US8)
Were the acceptance criteria met? | Yes: 24/24 Pytests passing; demand forecaster R² = 0.9650
What was demonstrated? | Streamlit delay classifier, RAG Logistics Assistant, Daily Briefing / Delay Scanner / Auto-Restock workflows
What stakeholder feedback was received? | [To Confirm]
What goes into the next backlog? | Hub feasibility study; KPI definition sheet; ML target realignment
Sprint Retrospective Template (project-wide)
Question | Answer
What went well? | Cross-track hand-offs worked: DS cleaned data and features fed DA, ML and GenAI on schedule
What blocked the team? | Missing supplier link and capacity field; differing revenue definitions between DA and DS
What should change next sprint? | Define KPIs and audit data fields at kickoff; align ML targets with business questions early
Action owners | PM for KPI definitions and kickoff audit; ML Lead for target realignment

## Quality & Closure
Quality Control Checklist
Check | Status | Evidence
Data validated against the Data Dictionary | Done | Validation by DS and DA tracks
Known data issues disclosed on dashboards | Done | Disclaimer for 1,626 shipments on cancelled orders
Automated tests passing | Pass | 24/24 Pytests (Appendix D)
Metrics reconciled or labelled | Done | Gross $19.1M vs Confirmed $14.44M labelled (Decision D-01)
Peer review of code | To Confirm | [To Confirm: review records]
Project Closure Checklist
Task | Status
Deliverables complete (dashboards, feature matrix, models, RAG assistant) | Done
Registers updated (risk, issue, change, decision, lessons learned) | Done
Repositories published (DA, DS, ML, GenAI) | Pending: insert links
PM report submitted | Pending
Presentation submitted | Pending